## Sheet1
Phase I: Trimester 1, 2025/2026
Activity | Week 1-2 | Week 3-4 | Week 5-6 | Week 7-8 | Week 9-10 | Week 11-12 | Week 13-14
1. Project Initiation
Topic Selection & Briefing | █
Problem Formulation (Occlusion) |  | █
2. Literature Review & Data
Reviewing Pose Models (MP vs YOLO) |  |  | █
Acquisition of REHAB24-6 Dataset |  |  |  | █
Drafting Literature Review (Chap 2) |  |  |  | █ | █
3. Methodology & Design
Designing "Strict Filter" Heuristics |  |  |  |  | █
Development Environment Setup (M1) |  |  |  |  | █
4. Implementation & Results
System Implementation (Python) | [5 empty] | █
Benchmarking & Data Analysis | [6 empty] | █
5. Documentation & Submission
Drafting Final Report (Chap 1-7) | █ | █ | █ | █ | █ | █ | █
FYP 1 Final Submission | [6 empty] | ★
Phase II: Trimester 2, 2026
Activity / Task | Week 1-2 | Week 3-4 | Week 5-6 | Week 7-8 | Week 9-10 | Week 11-12 | Week 13-14
1. Backend Pipeline & SOTA Evaluation
Batch Coordinate Processing (MediaPipe vs YOLO) | █
DTW Implementation & YOLOv8 Normalization |  | █
2. Advanced Methodology Refinement
Implementing Joint Angle Conversion |  |  | █
Ablation Studies & Environment Testing |  |  |  | █
3. System Integration & Deployment
Streamlit Core Dashboard UI Development |  |  |  |  | █
Conference Paper Drafting & Review |  |  |  |  | █
Project Poster & Demo Video Production | [5 empty] | █
4. Live Optimization & Finalization
Live Webcam Latency & FPS Optimization | [5 empty] | █
Real-time Coordinate & Angle Buffering | [5 empty] | █
5. Final Thesis Formulation
Formatting Corrections & Methodology Updates |  | █
Drafting Results & Discussion (Chap 4-7) | █ | █ | █ | █ | █ | █ | █
Final Formatting, Proofreading & Submission | █ | █ | █ | █ | █ | █ | ★